## Notes
Risk Profile
(FMEA)
1 | This analysis measures the level of risks associated with specific hazards and the likelihood of failure events occurring that could result in negative effects from those hazards.
2 | Complete the assessment by filling in the informational cells, then assigning their respective scores. (See Definitions worksheet.) This tool provides dropdown scores for a 10 point scale, but can also be used for a 5 point scale by ignoring values above 5. (See Scoring worksheet.)
This assessments is explained and demonstrated in the book Strategic Safety. Click on the button below to learn more about the book.
3 | A Risk Priority Number (RPN) is calculated by multiplying the Severity (SEV), Occurrence (OCC) and Detection (DET) scores. The resulting RPN is compared to the acceptability matrix to determine if and when corrective actions are required. (See Acceptability worksheet.) Acceptability scores are subjective, and can differ among industries and organizations based on individual risk tolerances.
4 | Upon completing the assessment, determine what actions will be taken. Score the changed conditions to determine what the new RPN number would be. The percent change is calculated ((New Value - Old Value) / Old Value * 100) to provide an estimate of the risk reduction.
Copyright © 2026 Sanovus, All Rights Reserved
Learn More 

## Scoring
Score | Severity (SEV) | Description | Score | Occurrence (OCC) | Description | Score | Detection (DET) | Description
9-10 (5) | Very High (Catastrophic) | Death or multiple serious injuries. Major External Environmental Impact. Major financial or operational impact. | 9-10 (5) | Very Likely (Frequent) | Occurs at least monthly. | 1-2 (1) | Very High | Controls will most likely detect a pending failure.
7-8 (4) | High (Critical) | Permanent disabling injury. Significant External Environmental Impact. Significant financial or operational impact. | 7-8 (4) | Likely (Often) | Occurs more than once a year. | 3-4 (2) | High | Controls have a good chance of detecting a pending failure.
5-6 (3) | Moderate (Serious) | Injury with temporary disability. Serious internal environmental impact. Moderate financial or operational impact. | 5-6 (3) | Probable (Occasional) | Occurs about once a year. | 5-6 (3) | Moderate | Controls may detect a pending failure.
3-4 (2) | Low (Minor) | Medical treatment only case. Minimal internal environmental impact. Minor financial or operational impact. | 3-4 (2) | Unlikely (Seldom) | Has or could occur once every 5 years. | 7-8 (4) | Low | Controls have a poor chance of detecting a pending failure.
1-2 (1) | Very Low (Negligible) | First aid case or no injury. Negligible internal environmental impact. Negligible financial or operational impact. | 1-2 (1) | Very Unlikely (Rarely) | Has not occurred in more than 5 years. | 9-10 (5) | Very Low | Controls probably will not detect a pending failure.
NOTE: The severity score measure the seriousness of a failure's effect on people, processes, or safety. The more serious the effect is, the higher the score. |  |  | NOTE: The Occurrence score is the likelihood that a specific cause will happen and result in a failure mode, given the current controls in place. |  |  | NOTE: The Detection score is the likelihood of an event being detected before it occurs. The scoring scale is reversed from the Severity and Occurrence score because a higher probability of detection presents a lower risk.
Scores: The top number range is used for a 10 point scale. The bottom scores, in parentheses, are used for a 5 point scale.

## Acceptability
RPN | Acceptability | Action
1 to 100 (1-14) | Acceptable (Low Risk) | Risk is low, or as low as reasonably practicable. Action is not required unless the risk level changes.
101 to 300 (15-29) | Tolerable (Mederate Risk) | Risk could be further mitigated. If action is taken, the timeline for completion should be reasonable .
301 to 500 (30-49) | Undesirable (High Risk) | Risk is higher than desired and actions needs to be taken at the earliest convenient opportunity to reduce the risk to a tolerable or acceptable level.
Above 500 (Above 49) | Unacceptable (Critical Risk) | Risk is too high and immediate action is required to reduce the risk to a tolerable or acceptable level.
Risk Priority Number (RPN) The top ranges are used for the 10 pt scale. The bottom ranges, in parentheses, are used for a 5 pt scale.

## Definitions
System, Area, or Job: | The plant or manufacturing system, area of the facility, or job being performed that presents a hazard(s).
Hazard: | A hazard presented by the system, area, or job, which can present multiple hazards.
Failure Event: | Potential failure(s) that might happen, related to the hazard, which could cause a harmful event.
Potential Effects: | The potential effect(s) of a failure event if it occurred. A severity score is assigned based on the potential effects.
Potential Causes: | Potential cause(s) of the failure event.
Existing Controls: | The controls currently in place designed to prevent the failure event from occurring. An occurrence score is assigned based on those controls. Occurrence is the likelihood of an event happening given the existing controls.
Detection Methods: | Existing alarms and other devices that would provide early detection or warning of a potential failure event. A detection score is assigned based on those controls. Detection is the likelihood of an event being detected before it occurs.

## Profile
Identification |  | Assessment | [8 empty] | Mitigation
System, Area, or Job | Hazard | Failure Event | Potential Effects | SEV | Potential Causes | Existing Controls | OCC | Detection Methods | DET | RPN | Mitigating Actions | SEV | OCC | DET | RPN | Risk Reduction
Totals | [9 empty] | 0 |  |  |  |  | 0